## Slide 1
BOARD OF DIRECTORS BRIEFING
PDPL Compliance Project: Plan, Budget, Approval
The plan, the cost and the approvals we need under Law 91/2025.
Tran My Phuc, DPO / IT & ISMS Manager
October 2026
Notes: Purpose: ask the Board to note and support the PDPL compliance plan that the General Manager is asked to approve. Open with the answer: Option A, start 05 Oct 2026, about $440 cash.

## Slide 2: The Short Answer
Approve Option A: start 05 October 2026, about $440 in cash.
1
Plan
27 tasks in 4 phases
05 Oct 2026 to 03 Feb 2027
Option A: full 34-day shift (recommended)
2
Cost
About $440 cash: AI tool, 4 months, with tax
Could fall to $0 if shared with Einvoices
Legal review: quote still to come
3
Decide
Approve Option A and the budget
GM confirms the flagged task owners
Note the three open items
Notes: One slide for readers who see only one. Plan: 27 tasks, 4 phases, 05 Oct 2026 to 03 Feb 2027 (Option A, recommended). Cost: only the AI tool has a figure, about $440 including an indicative 10% foreign contractor tax; it may fall to $0 if shared with the Einvoices subscription. Legal review needs a separate quote. Decide: approve Option A and the budget, confirm the task owners flagged for GM confirmation.

## Slide 3: Why Now, and What Is in Scope
Our own data first; client-side work is a separate workstream.
01 Jan 2026
Law 91/2025 is in force. Earlier filing reduces exposure under Decree 330/2026.
In scope
SGH Asia's own data
Employees, candidates, vendor and client contacts: HR, payroll, CRM, marketing.
Out of scope
Data processed for clients
Client-side engagements such as Topicus. Client contracts are covered on a later slide.
Phase 0 settles SGH Asia's classification: advisory (Art. 15-16) or processor (Art. 20-27).
Notes: Law 91/2025 has been in force since 01/01/2026. Scope is SGH Asia as a data controller for its own data subjects (employees, candidates, vendor and client contacts). Data processed for clients, for example the Topicus engagement, is excluded from this plan. Phase 0 issues a classification memo that settles whether SGH Asia is treated under the advisory articles (Decree 356/2025 Art. 15-16) or as a processor (Art. 20-27). Earliest filing reduces the exposure window under Decree 330/2026.

## Slide 4: Roadmap: 4 Phases, 27 Tasks
Option A, 05 Oct 2026 to 03 Feb 2027.
Oct
Nov
Dec
Jan
Feb
Phase 0
Governance & Kickoff
05 Oct – 18 Oct · 6 tasks
Phase 1
Discovery & Risk Assessment
05 Oct – 18 Nov · 6 tasks
Phase 2
Documentation & Contracts
18 Nov – 29 Dec · 5 tasks
Phase 3
Technical Measures & Filing
14 Dec – 03 Feb · 10 tasks
13 Jan 2027: DPO appointment filed with A05 Department. 03 Feb 2027: go-live sign-off.
Notes: Dates are Option A from the detailed plan. Phase 0 and Phase 1 start together on 05/10/2026. Phase 3 ends with the internal readiness audit and go-live sign-off on 03/02/2027. Milestones: DPO appointment notification to the A05 Department on 13/01/2027 (highest-priority filing), go-live sign-off 03/02/2027.

## Slide 5: Two Schedule Options
Option A is recommended; Option B only if Dec 2026 becomes a hard deadline.
Milestone | Option A: shift 34 days | Option B: contingency
DPO appointment filed with A05 | 13 Jan 2027 | 16 Dec 2026
Company-wide PDPL training | 23 Jan 2027 | 23 Dec 2026
Go-live sign-off | 03 Feb 2027 | 31 Dec 2026
Status | Recommended | Contingency only
External legal review (LTT & Lawyers, Phase 2) runs on its own turnaround under either option.
Notes: Option A is a full 34-day shift of the Sep-Dec 2026 plan and is recommended. Option B is contingency only: use it if completion in December 2026 becomes a hard requirement. Dates are the task deadlines in the detailed plan. External legal turnaround (LTT & Lawyers, Phase 2) is independent of internal capacity under either option.

## Slide 6: Budget: About $440 in Cash
One line has a figure. Everything else is no cash or waits for a quote.
$440
Estimated cash cost: AI tool, 4 months, including ~10% foreign contractor tax.
Could be $0 if shared with the Einvoices subscription.
No cash
Internal effort: 32.75 man-days
No cash
Translation: drafted in-house
No cash
PDPL training: by the DPO team
No cash
Tooling: M365 already in use
Finance
AI tool: $400 + ~$40 tax
Needs quote
External legal review (LTT)
Finance (Man Thi Loc) confirms the tax treatment before the figure is final.
Notes: Only the AI tool line has a figure: $100 per month for 4 months = $400, plus an indicative 10% Vietnam foreign contractor tax (about $40) = about $440, roughly $110 per month effective. The 10% rate is a planning assumption: Man Thi Loc (Finance) must confirm VAT and CIT treatment. The subscription may be shared with the Einvoices project, in which case the net incremental cost could be $0; not yet confirmed. External legal: LTT & Lawyers rate card outside the signed Appendix (Partner VND 5,000,000/hr, Associate VND 3,500,000/hr, Paralegal VND 2,500,000/hr); Agreement 25.12.08.LTT01 covers only the Topicus A05 dossier, so a new quote is needed for Phase 2 items 15 and 17. Translation, training and M365 need no cash.

## Slide 7: Internal Effort: 32.75 Man-Days
Man-days by phase and department. No cash outlay.
Chart: 
| Phase 0 | Phase 1 | Phase 2 | Phase 3
DPO Team | 3.5 | 6 | 5 | 6.5
IT-Security | 0 | 3.5 | 2 | 2.5
HR & OP | 0 | 1 | 1 | 1
Management | 0.25 | 0 | 0 | 0.5
32.75
man-days across 4 phases
DPO Team carries 21 of 32.75.
Peak load: Phase 1 and Phase 3, 10.5 each.
Two staff hold DPO and IT roles: about 14.5 man-days each.
Notes: Planning-level estimates derived from the 27-task plan, not measured actuals. DPO Team 21, IT-Security 8, HR & OP 3, Management 0.75. By phase: 3.75, 10.5, 8, 10.5. Hoang Le Viet Ha and Le Duc Tam hold dual capacity (DPO Team + IT-Security): about 14.5 man-days each over the 4 months; do not sum their rows independently. The estimates should be sanity-checked by Tran My Phuc, Hoang Le Viet Ha and Le Duc Tam against real bandwidth.

## Slide 8: Risks We Are Managing
Each risk has one owner action.
Legal turnaround
Items 15 and 17 depend on outside counsel (LTT & Lawyers)
Signed agreement covers the Topicus dossier only
Needed: a new quote
People
Two staff hold both DPO and IT roles: about 14.5 man-days each
Some task owners still need GM confirmation
Needed: GM confirms owners
Cost
AI tool may be shared with the Einvoices project
Tax treatment is a planning assumption
Needed: Finance confirmation
Notes: Three items need attention. External legal: items 15 and 17 depend on LTT turnaround and a new quote; this is the one dependency not solved by freed-up internal capacity, because the Topicus engagement concluded in May 2026. People: some Person in Charge entries are highlighted yellow in the plan and need GM confirmation; two staff hold dual capacity. Cost: the AI tool cost may be shared with the Einvoices subscription; tax treatment needs Finance confirmation.

## Slide 9: Client Contracts: When a DPA Applies
Scope: every client contract SGH Asia sells, where it acts as Data Processor (Law 91/2025/QH15).
No DPA
Signatory & team names
Name, title, signature, email, phone: personal data, but used only to form the contract. Art. 19.1(d): no consent; Art. 37 not triggered.
DPA required
Data in client systems
SGH Asia sees client data while delivering (HR, payroll, customers in Odoo). Agreement needed before access. Art. 2.8, 37.2(a).
DPA minimum content
Decree 356/2025/NĐ-CP, Art. 7
a
Purpose of access
b
Data types and data subjects
c
Processing period; delete after project
d
Legal basis
đ
Data protection duties
e
Data subject rights handling
g
Breach cooperation (72 h, Art. 23)
Next steps
1
Review Odoo contract template
2
Review ISO / AI advisory template
3
Confirm live or test data
Notes: Scope extension: contracts SGH Asia sells to clients (Odoo implementation, ISO 27001/42001 advisory, AI governance consulting, DPO outsourcing), where SGH Asia is a Data Processor. Names, titles and signatures of signatories and project members are personal data, but processing them to form the contract rests on Art. 19.1(d) and does not trigger Art. 37. The real risk: Odoo implementation gives SGH Asia access to client personal data (Art. 2.8, 37.2(a)). Next: add a Phase 2b "Commercial Client Contract PDPL Review" to the plan once the three inputs arrive.

## Slide 10: Decisions Requested
Three asks, then sign-off.
1
Approve Option A: start 05 Oct 2026, finish 03 Feb 2027
2
Approve the budget: about $440 cash for the AI tool
3
Confirm the task owners flagged for GM confirmation
Open items to track: LTT legal quote, Finance tax confirmation, Einvoices cost sharing.
Prepared by
Tran My Phuc
DPO / IT & ISMS Manager
Signature / date
Reviewed by
To be completed
Signature / date
Approved by
Pavel Poskakukhin
General Manager
Signature / date
Notes: Close on three asks, then the approval block. Prepared by Tran My Phuc (DPO / IT & ISMS Manager); reviewed by: to be completed; approved by Pavel Poskakukhin (General Manager). Open items to track: LTT legal quote, Finance tax confirmation, Einvoices cost sharing.